GOVERNMENT OF ANDHRA PRADESH

ABSTRACT

R&B- Roads & Bridge Works- Price Adjustment for Steel, Cement, Bitumen & POL and adoption of Overhead Charges- Accorded-Orders-issued.

-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-

TRANSPORT, ROADS & BUILDINGS(R.I) DEPARTMENT

G.O. Ms. No.35							Dated.28.02.2006

Read the following

1. Govt Memo No.5126/R.I(2)/2005-5,dated: 30.08.2005.

2. From the Engineer-in-Chief(R&B)Administration Letter.No. 67252/

TA1/AEE 1/2005, dt: 25.10.2005.

* * * * * * *

O R D E R:

In the Government Memorandum 1st read above, orders have been issued for adoption of Price Adjustment Clause in respect of Steel, Cement, Bitumen and POL for all Bridge Works costing more than Rs.50.00 lakhs and to be completed within a time schedule of more than 6 months. In supersession of the above instructions, the Government hereby issue the following comprehensive orders.

A) PRICE ADJUSTMENT:

- This Price Adjustment Clause shall apply for Steel, Cement, Bitumen and POL for all the road works & bridge works including ROBs/RUBs where the estimate contract value is Rs.50.00 lakhs and above and where the time schedule provided is 6 months and above.

- Price adjustment shall apply only for the work carried out within the agreement period and shall not apply to work carried out beyond the agreed period of completion.

- Price adjustment shall be calculated separately for the components of the payment for work done in the manner explained in paras (5) to (8) below.

- In the formula of price adjustment,  R, the value of work shall exclude Seigniorage charges, VAT and all over head charges.

- Adjustment Clause for cement component shall be as follows.

Price adjustment for increase or decrease in the cost of cement procured by the contractor shall be paid in accordance with the following formula.

Vc = 0.85 x Pc/100 x R x (Ci-Co)/Co

Vc = Increase or decrease in the cost of work done during the period

under consideration due to changes in the rates for cement.

Co = The All India Average Wholesale Price Index for cement on the

day 28 days prior to the closing date of submission of bids as published by the Ministry of Industrial Development, Government of India, New Delhi.

Ci = The All India Average Wholesale Price Index for cement on the

day 28 days prior to the last date of the measurement recorded to which a particular bill payment is related, as published by the Ministry of Industrial Development, Government of India , New Delhi.

Pc = Percentage of cement component of the work ( to be worked out

for each work and provided for in the bid document)

- Adjustment Clause for steel component shall be as follows:

Price adjustment for increase or decrease in the cost of steel procured by the contractor shall be paid in accordance with the following formula.

Vs = 0.85 x Ps/100 x R x (Si-So)/So

Vs = Increase or decrease in the cost of work done during the period

under consideration due to changes in the rates of steel.

So = The All India Average Wholesale Price Index for steel on the day

28 days prior to the closing date of submission of bids as published by the Ministry of Industrial Development, Government of India, New Delhi.

Si = The All India Average Wholesale Price Index for steel on the day

28 days prior to the last date of the measurement recorded to which a particular bill payment is related, as published by the Ministry of Industrial Development, Government of India,New Delhi.

Ps = Percentage of steel component of the work ( to be worked out for

each work and provided for in the bid document)

- Adjustment Clause for Bitumen component shall be as follows:

Price adjustment for increase or decrease in the cost of bitumen shall be paid in accordance with the following formula.

Vb = 0.85 x Pb/100 x R x (Bi-Bo)/Bo

Vb = Increase or decrease in the cost of work done during the period

under consideration due to changes in the rate for bitumen.

Bo = The Average Wholesale Price of bitumen at the refinery on the

day 28 days prior to date of submission of bids. The nearest refinery provided in the sanctioned estimate shall be considered.

Bi = The Average Wholesale Price of bitumen at the refinery on the

day 28 days prior to the last date of measurement recorded to which a particular bill payment is related.

Pb = Percentage of bitumen component of the work ( to be worked

out for each work and provided for in the bid document)

- Adjustment Clause for POL component shall be as follows:

Price adjustment for increase or decrease in the cost of POL shall be paid in accordance with the following formula.

Vf = 0.85 x Pf/100 x R x (Fi-Fo)/Fo

Vf = Increase or decrease in the cost of work done during the month

under consideration due to changes in the rate for POL.

Fo = The Average Wholesale Price  of High Speed Diesel(HSD) at the

existing consumer pumps of BPC at Hyderabad on the day 28 days prior to date of submission of bids.

Fi = The  Average Wholesale Price of High Speed Diesel(HSD) at the

existing consumer pumps of BPC at Hyderabad on the day 28 days prior to the last date of measurement recorded to which a particular bill payment is related.

Pf = Percentage of POL component of the work shall be 15%.

B)   OVER HEAD CHARGES:

  - For Bridge works, the overhead charges shall be adopted as 19% including component of VAT.

  - For road works, the overhead charges shall be adopted as 10% including component of VAT.

  - The components in the overhead charges include LA&LI/VAT/Sales

Tax/ Insurance/Compensation/Site Supervision/Quality Control charges and Bankers charges etc., as specified in MORTH Standard Data Book. No additional payment or reimbursement towards these components shall be claimed separately and none of them shall figure as part of estimate separately.

2.	Engineer-in-Chief(R&B),Administration shall take necessary action in the matter.

3.	This order issues with the concurrence of the Finance Department vide their U.O.No: 1201/106/Expr.PW/A2/06, dt.24-2-2006.

(BY ORDER AND IN THE NAME OF THE GOVERNOR OF ANDHRA PRADESH)

BINOY KUMAR

SECRETARY TO GOVERNMENT

To:

The Engineer-in-Chief(R&B) Administration, Hyderabad.

Copy to:

The Accounts General, AP, Hyderabad and others

/// f.b.o. ///

Sd/-x x x x

SECTION OFFICER

GOVERNMENT OF ANDHRA PRADESH

Office of the Engineer-in-Chief, PR, Hyderabad.

Endt. No. T1/29042/96, dated.21.03.2006

“Communicated”

Sd/- G.Krishna Murthy

Engineer-in-chief, PR, Hyd

To:

All the Superintending Engineers, PR, RWS &  RWS(P) in the State.

All the Executive Engineers, PR, RWS &  RWS(P) in the State.

Copy to: All the Chief Engineers, PR, for information.

Copy to SC/SF.

/// t. c . f . b. o ///

Dy. Executive Engineer(T)